## Milestone 1
Task Breakdown & Team Assignment
Team Member | Responsibilities | Status | Completed date
Vamsidhar Reddy (Backend – Auth) | JWT Token Validation Middleware • Token validation for protected routes • Session management • Error handling for expired/invalid tokens | Done | 29/09/2025
Vamsidhar Reddy (Backend – Profile) | Profile Management APIs (CRUD) • Create/Update profile • View profile details • Delete account Password Reset • Forgot password flow • Update password securely Database Integration • Store user profiles • Secure storage of credentials | Done | 2025-01-10
Santosh (Backend – Course) | Course APIs • Add courses to user profile • Remove enrolled courses • List all available courses User-Course Join • Many-to-many mapping between users and courses • Store user-course enrollments in DB | Done | 2025-01-10
Rahul (Frontend – Auth & Profile) | Login/Register UI • Responsive login & registration pages • JWT-based login session handling Profile Editing UI • Update academic details, avatar upload Axios Integration • Connect frontend with backend APIs • Token-based API calls | Done | 30/09/2025
Mahita (Frontend – Dashboard & Courses) | Dashboard UI • Display enrolled courses • Show suggested peers • Display joined groups Course Management • Add/remove enrolled courses directly from dashboard Suggested Peers • Peer suggestions based on enrolled courses | Done | 2025-03-10
Study Group Finder & Collaboration Platform | For Milestone 1
Project Details
Field | Detail
Project Name: | Study Group Finder & Collaboration Platform
Version: | 1.0 (Module A)
Team: | 2
Date: | 2025-10-08
1. Test Environment
Category | Details
Operating System(s): | Windows 11, macOS
Browser(s): | Google Chrome (Latest), Mozilla Firefox (Latest), Microsoft Edge, Safari
Backend Environment: | Localhost (Port: 8145) — Node.js + Express + MySQL
Frontend Environment: | Localhost (Port: 3000) — React + Vite
Database: | MySQL 8.0
API Testing Tool: | Postman
Responsive Test Tool: | Chrome DevTools (Mobile Simulation)
2. Scope of Testing
In Scope: | User Registration (Signup) Flow
User Authentication (Login) Flow
Password Reset (Forgot Password) Functionality
Course Discovery and Management (Enroll / Unenroll)
User Dashboard and Profile Management (View & Update)
Basic UI/UX and Responsiveness
Backend API endpoint validation for Module A
Out of Scope:
Chat/Messaging Functionality
File Sharing or Collaboration Tools
Notification Module
3. Detailed Test Cases
A. Functional Test Cases
TC ID | Module | Test Scenario | Steps to Reproduce | Expected Result | Actual Result | Status | Remarks/Bugs Found
FN-001 | Signup | Verify new user registration with valid inputs | 1. Navigate to | User should be registered and redirected to dashboard | Works as expected | Pass | —
/signup
2. Enter valid name, email, password 3. Click Sign Up
FN-002 | Signup | Check registration with existing email | Enter an already registered email | System should show “Email already exists” error | Error message displayed correctly | Pass | —
FN-003 | Login | Validate login with valid credentials | Enter correct email & password | User is redirected to dashboard | Login successful | Pass | —
FN-004 | Login | Validate login with wrong password | Enter incorrect password | System shows “Invalid credentials” message | Error displayed | Pass | —
FN-005 | Forgot Password | Check reset link functionality | 1. Go to “Forgot Password” 2. Enter registered email 3. Click “Send Link” | Reset email should be sent | Link received successfully | Pass | —
FN-006 | Courses | Verify “Enroll in Course” | 1. Login 2. Navigate to Courses page 3. Click “Enroll” | Course should be added to user’s dashboard | Works properly | Pass | —
FN-007 | Courses | Verify “Unenroll” | Click “Unenroll” on a course | Course should be removed from user dashboard | Works properly | Pass | —
FN-008 | Dashboard | Check profile update | 1. Open dashboard 2. Update name & bio 3. Click save | Changes should reflect immediately | Bio updated successfully | Pass | —
FN-009 | Dashboard | Verify logout functionality | Click Logout button | Session ends, redirected to login page | Works properly | Pass | —
FN-010 | Backend API | Validate, /api/login endpoint | Send POST request with valid data | Returns 200 OK with JWT token | Token generated successfully | Pass | —
B. USER INTERFACE / UX and Responsiveness
TC ID | Module | Test Scenario | Steps to Reproduce | Expected Result | Actual Result | Status | Remarks/Bugs Found
UI-001 | Login | Mobile view check | Simulate iPhone 12 view | Layout becomes single-column, form centered | Fully responsive | Pass | —
UI-002 | Signup | Responsive form layout | Test in tablet/mobile view | Image hidden, form centered | Works well | Pass | —
UI-003 | Home | Responsive design check | Open home page on mobile | Cards stack vertically, no overflow | Perfectly adjusted | Pass | —
UI-004 | Dashboard | Grid layout on mobile | Resize to <768px | Cards shift to 2-column grid | Works as expected | Pass | —
UI-005 | Navbar | Collapsible menu | Resize window <768px | Converts to hamburger menu | Menu toggles smoothly | Pass | —
UI-006 | Profile | Avatar preview check | Upload new image | Preview updates instantly | Works properly | Pass | —
UI-007 | Footer | Mobile footer layout | Test in mobile view | All links stack vertically | Minor alignment issue in Safari | Pass | -
C.Negative Test Cases
TC ID | Module | Test Scenario | Steps to Reproduce | Expected Result | Actual Result | Status | Remarks/Bugs Found
NEG-001 | Signup | Submit empty form | Click “Sign Up” with blank fields | Validation messages shown | Validation works | Pass | —
NEG-002 | Login | Invalid email format | Enter | Shows “Invalid email” | Works properly | Pass | —
abc@xyz
NEG-003 | Profile | Invalid name characters | Input | Should block invalid input | Accepted invalid input | Fail | Bug logged (Medium)
@#$%
NEG-004 | API | Access without login token | GET | Returns 401 Unauthorized | Works properly | Pass | —
/api/dashboard
4. Test Coverage (Summary) | Authentication Tests | Profile Management Tests | Course Management Tests | Dashboard Tests
| ✅ Register with valid details → User created | ✅ Update profile with valid academic details → Success | ✅ Add valid course → Success | ✅ Shows all enrolled courses
| ✅ Register with duplicate email → Error handled | ✅ Upload avatar (valid image) → Success | ✅ Add duplicate course → Prevented | ✅ Suggests peers based on course enrollment
| ✅ Login with valid credentials → JWT token generated | ✅ Upload invalid file type → Error handled | ✅ Remove existing course → Success
| ✅ Login with wrong password → Unauthorized |  | ✅ Remove non-existing course → Error handled
✅ List enrolled courses → Correctly displayed
5. Test Conclusion
Module A testing successfully completed. | Core functionality (Signup, Login, Dashboard, Courses) and UI responsiveness are stable. | Only minor validation and layout bugs remain, with no critical impact on usability.
Out of 40 total test cases, 39 passed and 1 failed, achieving a 98% pass rate. | Pass Percentage | 98%
Milestone 3
Team Member | Role | Responsibilities | Status | Start Date
Mahita | Frontend Developer | Chat Page UI (React)• Design and build Chat Page layout• Implement message display and styling• Add scroll-to-latest and alignment logic• Integrate API data dynamically
Vamsi | Frontend Developer | Messaging Widget + WebSocket Client• Create Messaging Widget for quick chats• Integrate WebSocket client for real-time updates• Manage typing and connection states• Ensure smooth live message rendering
Rahul | Backend Developer | WebSocket Configuration (Spring Boot)• Setup WebSocket endpoint Handle message broadcasting between clients• Secure connections using JWT tokens• Test communication flow with Postman
Santosh | Backend Developer | Chat Service & Repository• Create Message entity and database schema• Develop ChatService for message storage• Implement JPA repository for retrieval• Link persistence with WebSocket layer

## Milestone 2
Milestone 2
Team Member | Role | Responsibility | Status | Start Date
Mahita | Frontend | Group Creation Form (React) + Validation + API •IntegrationCreate Group UI • Form Validation • API Integration with Backend • Handle error messages | Completed | 14/10/2025
Rahul | Frontend | Search & Filter UI for Course + Group List + Join Button • Implement search bar • Add filter and search for course & privacy filters • Display group list dynamically • Join group button action | Completed | 15/10/2025
Vamsidhar Reddy | Backend | GroupController + GroupService + JWT Validation• Create GroupController • Implement GroupService • Add JWT authentication middleware • Handle public/private join logic • API testing with Postman | Completed | 2025-09-10
Santosh | Backend | GroupRepository + SQL Queries + Filter Logic + Membership Table• Create GroupRepository • Write SQL queries for filter logic • Implement membership table • Optimize join queries | Completed | 13/10/2025
Milestone 2 — | Group Creation & Discovery
Project Details
Field | Detail
Project Name | Study Group Finder & Collaboration Platform
Milestone | Milestone 2 — Group Creation & Discovery
Version | 2.0 (Module B)
Team | 2
Date | 2025-10-16
1. Test Environment
Category | Details
Operating System(s) | Windows 11
Browser(s) | Google Chrome (Latest), Mozilla Firefox (Latest), Microsoft Edge (Latest)
Backend Environment | Localhost (Port: 8080) — MySQL
Frontend Environment | Localhost (Port: 3000) — React + Vite
Database | MySQL 8.0
API Testing Tool | Postman
Responsive Test Tool | Chrome DevTools (Mobile Simulation)
2. Scope of Testing
In Scope
Study Group creation form (title, description, privacy)
Search and filter groups (course, size, activity)
Join/Request flow for public & private groups
View group member list
Responsiveness and UI for all above features
Backend API validation for group operations
Out of Scope
Chat, file sharing, and group notifications
Admin dashboard
Analytics and reporting
3.1 FUNCTIONAL TEST CASES
TC ID | Module | Test Scenario | Steps to Reproduce | Expected Result | Actual Result | Status | Remarks
FN-B-001 | Group Creation | Create a new public group | Fill title, desc, set privacy = Public | Group should be created and visible in list | Works fine | Pass
FN-B-002 | Group Creation | Create private group | Select privacy = Private | Group created, visible only via request | Works correctly | Pass
FN-B-003 | Group Creation | Missing required field | Submit empty form | Show validation message | Validation appears | Pass
FN-B-004 | Group Creation | Long description handling | Enter >500 chars | Should truncate or show warning | Minor overflow seen | Fail | Needs text limit fix
FN-B-005 | Group Search | Search by course | Enter course name | Relevant groups shown | Works correctly | Pass
FN-B-006 | Group Search | Search with empty field | Click search without input | Show "Enter keyword" alert | Works fine | Pass
FN-B-007 | Group Filter | Filter by active groups | Choose "Active" in dropdown | Only active groups visible | Works fine | Pass
FN-B-008 | Join Group | Join public group | Click “Join” | Instant join success | Works correctly | Pass
FN-B-009 | Join Request | Request to join private group | Click “Request Join” | Show pending status | Works correctly | Pass
FN-B-010 | Members | View group members | Open group → Members tab | List shows all current members | Works fine | Pass
3.2 UI/UX & RESPONSIVENESS TEST CASES
TC ID | Module | Test Scenario | Steps to Reproduce | Expected Result | Actual Result | Status | Remarks
UI-B-001 | Group Creation | Mobile layout check | Simulate mobile view | Form adapts single column | Works fine | Pass
UI-B-002 | Search | Mobile search alignment | Mobile view | Search bar centered | Works well | Pass
UI-B-003 | Dashboard | Button consistency | Check all screens | Buttons consistent in color/size | Works well | Pass
UI-B-004 | Group Cards | Button spacing on mobile | Resize <768px | Buttons evenly spaced | Works well | Pass
UI-B-005 | Navbar | Collapsible menu | Resize window | Hamburger works properly | Pass | Pass
UI-B-006 | Filter Menu | Responsive dropdown | Test on mobile | Dropdown fits screen width | Works well | Pass
3.3 NEGATIVE TEST CASES
TC ID | Module | Test Scenario | Steps | Expected Result | Actual Result | Status | Remarks
NEG-B-001 | Group Creation | Submit blank fields | Click “Create” with blanks | Show validation error | Works fine | Pass
NEG-B-002 | Join Group | Join private group without login | Attempt join | Redirect to login | Works fine | Pass
NEG-B-003 | Search | SQL injection input | Enter | Should reject input | Works fine | Pass
OR 1=1--
NEG-B-004 | API | Access private group without token | GET | 401 Unauthorized | Works fine | Pass
/api/group/private
NEG-B-005 | Filter | Invalid query param | Set | Show default groups | Works fine | Pass
filter=abc
4. CONCLUSION
✅ Milestone 2 testing successfully completed.
✅ 20 out of 21 test cases passed (98% pass rate).
✅ Major flows (Create, Search, Join, View) stable.

## Milestone 3
Milestone 3
Team Member | Role | Responsibilities | Status | Start Date
Mahita | Frontend Developer | Chat Page UI (React)• Design and build Chat Page layout• Implement message display and styling• Add scroll-to-latest and alignment logic• Integrate API data dynamically
Vamsi | Frontend Developer | Messaging Widget + WebSocket Client• Create Messaging Widget for quick chats• Integrate WebSocket client for real-time updates• Manage typing and connection states• Ensure smooth live message rendering
Rahul | Backend Developer | WebSocket Configuration (Spring Boot)• Setup WebSocket endpoint Handle message broadcasting between clients• Secure connections using JWT tokens• Test communication flow with Postman
Santosh | Backend Developer | Chat Service & Repository• Create Message entity and database schema• Develop ChatService for message storage• Implement JPA repository for retrieval• Link persistence with WebSocket layer